## Master Checklist
Done | Category | Item | When | Owner | Notes
☐ | A. Physical Space | Studio deep-cleaned and arranged for the start of the year | 2 weeks out | Guide
☐ | A. Physical Space | Workstation arrangement set (returners revisited, new learners assigned) | 1 week out | Guide
☐ | A. Physical Space | Name cards printed and placed at each workstation | Night before | Guide
☐ | A. Physical Space | Cubby labels updated for current roster | 1 week out | Guide
☐ | A. Physical Space | Reading nook stocked with at least 30 books at varied reading levels | 2 weeks out | Guide
☐ | A. Physical Space | Materials shelves organized and labeled | 1 week out | Guide
☐ | A. Physical Space | Quiet corner / fidget corner / sensory tools set up | 1 week out | Guide
☐ | A. Physical Space | Plants watered, trash empty, surfaces wiped | Night before | Guide
☐ | A. Physical Space | Whiteboard markers tested + spares stocked | 1 week out | Guide
☐ | A. Physical Space | Full daily schedule printed at poster size and mounted prominently | 1 week out | Guide
☐ | A. Physical Space | Hero's Journey wheel poster created and mounted | 1 week out | Guide
☐ | A. Physical Space | Six blank Standard of Excellence poster templates mounted | 1 week out | Guide | Math · ELA · Quest · Town Hall · Snack · Maintenance
☐ | A. Physical Space | Day 1 Thinking Puzzle posted near cubbies before learners arrive | Night before | Guide
☐ | A. Physical Space | Studio Contract running list paper mounted | Night before | Guide | Will fill in Week 1 Town Hall
☐ | A. Physical Space | Rules of Engagement placeholder ready to fill in Week 2 | 3 days out | Guide
☐ | A. Physical Space | Leadership Roles board mounted (roles defined, sign-up area prepped) | 3 days out | Guide
☐ | A. Physical Space | Topic box for Town Hall labeled and placed | 3 days out | Guide
☐ | A. Physical Space | Compass Keeper notebook + Quote Keeper notebook ready | 3 days out | Guide
☐ | B. Documents Printed | Personal Working Guide blank template — printed (N learners + 4 spares) | 1 week out | Guide
☐ | B. Documents Printed | Habit & Character Goals notebooks — one per learner | 2 weeks out | Guide
☐ | B. Documents Printed | First ICEE Survey forms — printed for Week 1 | 1 week out | Guide | If going paper
☐ | B. Documents Printed | First 360 Reflection prompts printed for Week 1 | 1 week out | Guide
☐ | B. Documents Printed | Trading Card template (for Week 2 Day 1) | Week 1 mid-week | Guide
☐ | B. Documents Printed | Studio Contract personal copy template (Week 6 signing) | Week 5 | Guide
☐ | B. Documents Printed | Welcome packet for each learner | 1 week out | Guide | Schedule, week-1 heads-up, family welcome letter copy
☐ | B. Documents Printed | Week 1 Day 1–5 minute-by-minute pages printed or on tablet | Night before | Guide
☐ | B. Documents Printed | Compass check protocol card | 1 week out | Guide
☐ | B. Documents Printed | Leadership Roles full descriptions printed | 1 week out | Guide
☐ | B. Documents Printed | Character Traits working list printed (for callouts coaching) | 1 week out | Guide
☐ | B. Documents Printed | Standard of Excellence framework reference card | 1 week out | Guide | SOUND/LOOK/FEEL/SIGN
☐ | B. Documents Printed | Sticky notes (multiple colors, multiple sizes) | 2 weeks out | Guide
☐ | B. Documents Printed | Index cards (pack of 100+) | 2 weeks out | Guide
☐ | B. Documents Printed | Large chart paper / butcher paper roll | 2 weeks out | Guide
☐ | B. Documents Printed | Whiteboard markers (assorted colors) | 2 weeks out | Guide
☐ | B. Documents Printed | Tape (masking, painter's, double-sided) | 2 weeks out | Guide
☐ | B. Documents Printed | Markers, colored pencils, scissors (per workstation) | 2 weeks out | Guide
☐ | B. Documents Printed | Soft ball (for name games & circle games) | 2 weeks out | Guide
☐ | B. Documents Printed | Timer (visible to whole studio — physical preferred) | 2 weeks out | Guide
☐ | C. Digital Setup | IXL accounts created/verified for every learner | 1 week out | Guide
☐ | C. Digital Setup | IXL placement reviewed and starting level set for each learner | 1 week out | Guide
☐ | C. Digital Setup | Rocket Math accounts verified, starting levels set | 1 week out | Guide
☐ | C. Digital Setup | NoRedInk accounts (or final ELA stack) set up | 1 week out | Guide
☐ | C. Digital Setup | Night Zookeeper accounts (or other writing tool) | 1 week out | Guide
☐ | C. Digital Setup | Nessy accounts for learners with reading support | 1 week out | Guide
☐ | C. Digital Setup | Kids A-Z accounts set up | 1 week out | Guide
☐ | C. Digital Setup | Typing Club accounts ready | 1 week out | Guide
☐ | C. Digital Setup | Every chromebook/computer tested with every login | 3 days out | Guide | Not just one — actually every device + every login
☐ | C. Digital Setup | Chargers identified and accessible at each workstation | 3 days out | Guide
☐ | C. Digital Setup | Studio Google Drive folder structure for the year created | 2 weeks out | Guide
☐ | C. Digital Setup | Parent email list current and verified | 2 weeks out | Guide
☐ | C. Digital Setup | ICEE Survey published (Google Form OR confirmed paper workflow) | 1 week out | Guide
☐ | C. Digital Setup | Studio guide companion site bookmarked on every device | 1 week out | Guide
☐ | C. Digital Setup | Tablet/camera identified for Tribe Photographer role | 2 weeks out | Guide
☐ | C. Digital Setup | Photo/video consent forms drafted | 2 weeks out | Guide
☐ | D. Curriculum | Math: IXL placement reviewed for each learner | 1 week out | Guide
☐ | D. Curriculum | ELA software stack finalized (which tools used which days) | 2 weeks out | Guide
☐ | D. Curriculum | Civilization curriculum chosen and Week 1–6 sketched | 3 weeks out | Guide
☐ | D. Curriculum | First Read-Along book chosen and obtained | 2 weeks out | Guide | One per learner if budget allows
☐ | D. Curriculum | Friday Improv schedule confirmed with Clare | 2 weeks out | Guide + Clare
☐ | D. Curriculum | Pedro language session logistics confirmed | 2 weeks out | Guide + Pedro | Day, time, format
☐ | D. Curriculum | Week 1 Day 1 Quest activity materials (Ordinary World constellation) | 1 week out | Guide
☐ | D. Curriculum | Week 1 Day 2 Quest (Partner Interview) prompts prepared | 1 week out | Guide
☐ | D. Curriculum | Week 2 Trading Card materials & template ready | Week 1 | Guide
☐ | D. Curriculum | Work It Out tool reference materials obtained from Spark guide | 1 week out | Guide + Spark
☐ | D. Curriculum | Activities & Games library reviewed; 8–10 specific games picked for first 2 weeks | 1 week out | Guide
☐ | E. Cross-Studio | All-school calendar coordinated | 3 weeks out | School lead + guides | BTT weeks, adventure days, school-wide events
☐ | E. Cross-Studio | School-Wide Town Hall schedule and weekly format confirmed | 2 weeks out | All guides
☐ | E. Cross-Studio | Week 3 (Cross-Studio Week) coordinated with Spark, D1, Exploration | 2 weeks out | All guides
☐ | E. Cross-Studio | Spark Buddy / D1 Mentor / Exploration Connector framing aligned | 2 weeks out | All guides
☐ | E. Cross-Studio | Adventure Days proposed dates locked with school leadership | 3 weeks out | School lead
☐ | F. Learner Prep | Learner roster verified (names, pronouns, emergency contacts) | 2 weeks out | Guide + admin
☐ | F. Learner Prep | Accommodation plans reviewed for learners with documented needs | 2 weeks out | Guide + parents | Privately, with parents
☐ | F. Learner Prep | Allergy / dietary notes collected, posted privately for guide reference | 1 week out | Guide + admin
☐ | F. Learner Prep | Returner conversations / informal touchbase before Day 1 | 1 week out | Guide
☐ | F. Learner Prep | New learner welcome calls / brief intros with families | 2 weeks out | Guide
☐ | F. Learner Prep | Notes about learner relationships flagged | 1 week out | Guide | Seating needs, social dynamics
☐ | G. Parent Comm | Welcome letter sent to families | 3 weeks out | Guide
☐ | G. Parent Comm | Yearly calendar shared | 3 weeks out | Guide
☐ | G. Parent Comm | Schedule (the daily one) shared with families | 2 weeks out | Guide
☐ | G. Parent Comm | Quick BTT overview sent | 2 weeks out | Guide | What we're building in the first 6 weeks and why
☐ | G. Parent Comm | Photo/video consent forms sent and tracked | 2 weeks out | Guide
☐ | G. Parent Comm | Family Communication Norms document sent | 2 weeks out | Guide | When/how to reach the guide
☐ | G. Parent Comm | First Friday parent update email drafted | 1 week out | Guide | Will customize each Friday
☐ | G. Parent Comm | Exhibition Day Save-the-Date sent to families | 3 weeks out | Guide | Week 6 Friday
☐ | H. Adventure Days | Library Day — walking route scouted and timed | 3 weeks out | Guide
☐ | H. Adventure Days | Library Day — library contact made; visit scheduled | 3 weeks out | Guide
☐ | H. Adventure Days | Library Day — permission slips drafted, sent, collected | 2 weeks out | Guide
☐ | H. Adventure Days | Library Day — walking safety norms reviewed with all-school | 2 weeks out | All guides
☐ | H. Adventure Days | Acton Games — date locked with all studios | 4 weeks out | All guides
☐ | H. Adventure Days | Acton Games — event list / format developed | 3 weeks out | All guides
☐ | H. Adventure Days | Acton Games — D2 learner roles in planning identified | 2 weeks out | Guide
☐ | H. Adventure Days | Cardboard Boat — pool secured | 6 weeks out | Guide + Pedro | Check Pedro's contacts first
☐ | H. Adventure Days | Cardboard Boat — liability / waiver forms drafted and approved | 4 weeks out | Guide + admin
☐ | H. Adventure Days | Cardboard Boat — pool day permission slips sent to families | 3 weeks out | Guide
☐ | H. Adventure Days | Cardboard Boat — Pedro's existing resources requested and reviewed | 4 weeks out | Guide
☐ | H. Adventure Days | Cardboard Boat — cardboard + tape sourced (large quantity) | 3 weeks out | Guide
☐ | H. Adventure Days | Cardboard Boat — water safety norms confirmed | 3 weeks out | Guide + admin | Lifeguards, parent helpers
☐ | H. Adventure Days | Cardboard Boat — transportation to pool arranged | 3 weeks out | Guide + admin
☐ | I. Lip Dub | Camera / phone identified for filming | Week 3 | Guide | With stabilizer if possible
☐ | I. Lip Dub | Reference lip dub videos collected | Week 3 | Guide | 2–3 great examples
☐ | I. Lip Dub | Indoor + outdoor filming route mapped | Week 4 | Guide + studio
☐ | I. Lip Dub | Music licensing checked | Week 4 | Guide | If final video will be public-shared
☐ | I. Lip Dub | Backup audio source confirmed for filming days | Week 4 | Guide | Bluetooth speaker, charged
☐ | I. Lip Dub | Photo/video consent confirmed for every learner appearing | Week 4 | Guide
☐ | J. Exhibition | Save-the-date sent to families | 3 weeks out | Guide
☐ | J. Exhibition | Final invitation with format sent to families | Week 5 | Guide | 1 week out
☐ | J. Exhibition | Spark + Exploration participation coordinated | 2 weeks out | All guides
☐ | J. Exhibition | Refreshments planned and assigned | Week 5 | Guide + families
☐ | J. Exhibition | AV setup tested (Lip Dub playback, sound) | Week 6 | Guide
☐ | J. Exhibition | Final Studio Contract printed | Week 6 Tuesday | Guide | Large copy for wall + personal copies
☐ | J. Exhibition | Launch Circle locations mapped in the studio | Week 6 Wednesday | Guide + studio
☐ | J. Exhibition | Photographer assigned | Week 6 | Guide | Parent volunteer or learner
☐ | K. Guide Personal | Guide's own Personal Working Guide filled out | 1 week out | Guide | The model you'll share Day 1
☐ | K. Guide Personal | Day 1 morning launch script reviewed and internalized | 3 days out | Guide | Not memorized — felt
☐ | K. Guide Personal | Day 2 (Equity vs. Equality) and Day 4 (Boundaries) launches reviewed | 3 days out | Guide
☐ | K. Guide Personal | Town Hall #1 narration moves rehearsed | 3 days out | Guide
☐ | K. Guide Personal | Compass check role-play with co-guide | 1 week out | Guide + co-guide | Or solo dry-run
☐ | K. Guide Personal | Energy management plan: snacks, water, breaks | 1 week out | Guide
☐ | K. Guide Personal | Co-guide handoffs and communication norms agreed | 1 week out | Guide + co-guide
☐ | K. Guide Personal | Your own Habit & Character Goal for the first 6 weeks written | 1 week out | Guide
☐ | L. Weekly Rituals | ICEE Survey end-to-end tested | 1 week out | Guide | Form → tally → posted result
☐ | L. Weekly Rituals | Town Hall topic box workflow confirmed | 1 week out | Guide | Where it lives, who reads it
☐ | L. Weekly Rituals | Friday Share Chair process clarified | 1 week out | Guide | Who picks the chair, where it sits
☐ | L. Weekly Rituals | Character Callouts rhythm prepared | 3 days out | Guide | Guide goes first the first 3 days
☐ | L. Weekly Rituals | Thinking Puzzle posting workflow defined | 3 days out | Guide | Who posts, when, where
☐ | L. Weekly Rituals | Studio Maintenance zones drawn / mapped | 3 days out | Guide

## Summary
BTT Pre-Check Summary
D2 Build the Tribe · v1.0
Category | Items | Done | % Complete
A. Physical Space | 18 | 0 | 0%
B. Documents Printed | 20 | 0 | 0%
C. Digital Setup | 16 | 0 | 0%
D. Curriculum | 11 | 0 | 0%
E. Cross-Studio | 5 | 0 | 0%
F. Learner Prep | 6 | 0 | 0%
G. Parent Comm | 8 | 0 | 0%
H. Adventure Days | 14 | 0 | 0%
I. Lip Dub | 6 | 0 | 0%
J. Exhibition | 8 | 0 | 0%
K. Guide Personal | 8 | 0 | 0%
L. Weekly Rituals | 6 | 0 | 0%
TOTAL | 126 | 0 | 0%
How to use:
Change "☐" to "☑" in the Done column on the Master Checklist sheet to mark items complete.
Summary updates automatically.